## Sheet1
Milestone | Description | Due date
Milestone 1 | Extended proposal | 2026-02-12
Milestone 2 | Progess Report 1 | 2026-03-11
Milestone 3 | Progess Report 2 | 2026-03-25
Milestone 4 | First full draft | 2026-04-08
Milestone 5 | Final paper | 2026-04-22
Milestone 6 | Conference version of paper | 2026-04-27

## Sheet2
Internal Task | Description | Target Date
Background Research Completion | Finalize literature review and related work | 2026-02-20
Data Cleaning Completion | Clean dataset, handle missing values, encode variables | 2026-02-25
Feature Engineering Completion | Create rolling stats, goal differentials, form metrics | 2026-03-02
Baseline Model Completion | Implement multinomial logistic regression | 2026-03-07
Experiment Setup Completion | Finalize train-test split and evaluation framework | 2026-03-10
ML Model Implementation Completion | Implement Decision Tree, Random Forest, XGBoost | 2026-03-18
Hyperparameter Tuning Completion | Perform cross-validation and grid search | 2026-03-22
Experiment Runs Completion | Run full training and testing across models | 2026-03-28
Experiment Analysis Completion | Generate metrics, ROC curves, confusion matrices | 2026-04-03
Code Completion | Finalized, cleaned, documented codebase | 2026-04-06